## Sheet1
Site Reference | Site Name | LDP reference | Site Address | Easting | Northing | Site Area (Hectares) | Year Added To HLA | LDP / Windfall / Other | Planning Status | Other detail | Main Planning Application Reference(s) | Planning Approval Date | Construction status | Year construction started | Site Capacity | Remaining capacity | Completions in the Audit Year | Total completions to date | Programming_Y1 | Programming_Y2 | Programming_Y3 | Programming_Y4 | Programming_Y5 | Programming_Y6 | Programming_Y7 | Programming_Y8 | Programming_Y9 | Programming_Y10 | Pipeline Timeframe | Tenure | Number Market | Number Affordable | Number flats | Number houses | Deliverability status | Constraint notes | Action required | Owner | Developer | Greenfield / Brownfield | VDL | Self Build | Dispute | Demolition
WD0355A | LITTLEMILL DISTILERY (NORTH EAST) | H2(25) | LITTLEMILL DISTILERY (NORTH EAST), BOWLING | 244133 | 673777 | 0.45 | 1996 | LDP | No Consent |  | 03/334 |  | Not yet started |  | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 33 | 0 |  |  | Constrained | Physical: high risk of surface water flooding. Some buildings on site require demolition. | Planning Authority to seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | NK | Brownfield | Yes |  | No dispute
WD0392 | 354-394 DUMBARTON ROAD | H2(10) | 354-394 DUMBARTON ROAD, CLYDEBANK | 248943 | 670790 | 0.17 | 1999 | LDP | No Consent | @2025 Electronic advertising boards erected on site |  |  | Not yet started |  | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | 0 | 10 |  |  | Constrained | Ownership: Erection of electronic billboards indicates lack of intention to develop in short term. | Seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | NK | Brownfield | Yes |  | No dispute
WD0427A | KEIL SCHOOL PHASE 2 | H2(32) | KEIL SCHOOL PHASE 2, DUMBARTON | 238664 | 675110 | 1.54 | 2001 | LDP | No Consent |  |  |  | Not yet started |  | 51 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 51 | 0 |  |  | Constrained | No known constraints | Site owner currnetly investigating site constraints. Planning Authority and owner to continue discussions as necessary. Planning Authority to continue to monitor site. | Private Owner | NK | Brownfield | No |  | No dispute
WD0476 | CARLESS OIL DEPOT | H2(33) | CARLESS OIL DEPOT, OLD KILPATRICK | 246884 | 671939 | 11.77 | 2004 | LDP | No Consent | 2010 plan has larger site identified with capacity of 400. 2020 plan identifies smaller part of site for 50 units. |  |  | Not yet started |  | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 50 | 0 |  |  | Constrained | Land Use Status: Allocated in LDP but no active planning permission. Physical: currently no adoptable vehical access to site | Planning Authority to continue to monitor site. | Private Owner | NK | Brownfield | No |  | No dispute
WD0524 | 14-20 GOLFHILL DRIVE | H2(48) | 14-20 GOLFHILL DRIVE, BONHILL | 239865 | 680262 | 0.1 | 2006 | LDP | Consented (full) | SHIP SITE | DC22/154/FUL | 2023-11-07 | Not yet started |  | 7 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | 0 | 7 |  |  | Deliverable | No known constraints | Planning authority to continue to monitor site. | Housing Association | DUNBRITTON HA | Brownfield | No |  | No dispute
WD0614 | BONHILL GAP SITE CAMBELL STREET |  | BONHILL GAP SITE CAMBELL STREET, BONHILL | 240279 | 679439 | 0.24 | 2025 | Windfall | Consented (full) | 2025/30 SHIP priority site. Grant from Affordable Housing Supply Programme | DC24/080/FUL | 2024-09-01 | Not yet started |  | 11 | 11 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | short-term | Affordable | 0 | 11 |  |  | Deliverable | No known constraints | Planning authority to continue to monitor site. | West Dunbartonshire Council | WDC | Greenfield | No |  | No dispute
WD0477 | THOR CERAMICS STANFORD ST | H2(53) | THOR CERAMICS STANFORD ST, CLYDEBANK | 250202 | 670241 | 1.34 | 2004 | LDP | No Consent |  |  |  | Not yet started |  | 92 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 92 | 0 |  |  | Constrained | No known constraints, however development has not come forward | Seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | NK | Brownfield | Yes |  | No dispute
WD0615 | BONHILL GAP SITE BRAEHEAD |  | BONHILL GAP SITE BRAEHEAD, BONHILL | 240633 | 679077 | 0.74 | 2025 | Windfall | Consented (full) | 2025/30 SHIP priority site. Grant from Affordable Housing Supply Programme | DC24/096/FUL | 2025-01-31 | Not yet started |  | 17 | 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | 0 | 17 |  |  | Deliverable | No known constraints | Planning authority continue to monitor site delivery | West Dunbartonshire Council | WDC | Greenfield | No |  | No dispute
WD0616 | BONHILL GAP SITE O'HARE |  | BONHILL GAP SITE O'HARE, BONHILL | 240279 | 679439 | 0.19 | 2025 | Windfall | Consented (full) | 2025/30 SHIP priority site. Grant from Affordable Housing Supply Programme | DC24/161/FUL | 2025-03-04 | Not yet started |  | 6 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | 0 | 6 |  |  | Deliverable | No known constraints | Planning authority continue to monitor site delivery | West Dunbartonshire Council | WDC | Greenfield | No |  | No dispute
WD0494 | CARLEITH | H2(55) | CARLEITH, CLYDEBANK | 248123 | 673121 | 0.67 | 2006 | LDP | No Consent |  |  |  | Not yet started |  | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 8 | 0 |  |  | Constrained | No known constraints | Seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | PLOTS | Brownfield | No |  | No dispute
WD0501 | LEVENBANK STREET | H2(41) | LEVENBANK STREET, JAMESTOWN | 239821 | 681066 | 2.86 | 2006 | LDP | No Consent | Council as land owner is in discussions with potential developer. Site is accessed by an unadoppted road, however the road is also owned by the council. Discussions with Road and planning services taking place to resolve this. |  |  | Not yet started |  | 86 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 86 | 0 |  |  | Deliverable with constraints | Land Use Status: Allocated in LDP but no active planning permission. Disucssions taking place between owner (Council) and potential developer. Physical: Access road is not adopted | WDC Roads and Planning continue to work with potential developer on access solution | West Dunbartonshire Council | NK | Greenfield | No |  | No dispute
WD0518A | HEATHER AVENUE - REMAINDER | H2(62) | HEATHER AVENUE - REMAINDER, ALEXANDRIA | 239198 | 680603 | 2.51 | 2007 | LDP | No Consent |  |  |  | Not yet started |  | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 84 | 0 |  |  | Constrained | Physical: Some areas of site at risk of flooding - however significant portion of the site under no risk from flooding Land Use Status: Allocated in LDP2, but no active planning permission | Planning authority to continue to monitor site. | West Dunbartonshire Council | NK | Brownfield | Yes |  | No dispute
WD0528 | N DOUGLAS ST/FORMER UNITY CLUB | H2(10) | N DOUGLAS ST/FORMER UNITY CLUB, CLYDEBANK | 250197 | 669660 | 0.06 | 2008 | LDP | No Consent |  | DC07/207/FUL |  | Not yet started |  | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 12 | 0 |  |  | Constrained | No known constraints, however development has not come forward | Seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | NK | Brownfield | No |  | No dispute
WD0463A | QUEENS QUAY - EAST YARD | H2(11) | QUEENS QUAY - EAST YARD, CLYDEBANK | 249760 | 669781 | 4.28 | 2003 | LDP | Consented (PPiP) |  | DC15/234 | 2016-08-28 | Not yet started |  | 344 | 344 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | medium-long-term | Market | 344 | 0 |  |  | Deliverable with constraints | Financial: industry are citing issues with the marketability of the site. | Continue participating in Scottish Governments stalled sites programme. Planning and Regneration teams within council to work to promote West Dunbartonshire as location for housebuilding | Private Owner | NK | Brownfield | Yes |  | Disputed by Homes for Scotland
WD0463B | QUEENS QUAY - PLOTS 8-12 | H2(11) | QUEENS QUAY - PLOTS 8-12, CLYDEBANK | 249377 | 670039 | 8.53 | 2003 | LDP | Consented (PPiP) |  | DC15/234 | 2016-08-28 | Not yet started |  | 468 | 468 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | medium-long-term | Market | 468 | 0 |  |  | Deliverable with constraints | Financial: industry are citing issues with the marketability of the site. | Continue participating in Scottish Governments stalled sites programme. Planning and Regneration teams within council to work to promote West Dunbartonshire as location for housebuilding | Private Owner | NK | Brownfield | No |  | Disputed by Homes for Scotland
WD0463C | QUEENS QUAY - PLOT 7 | H2(49) | QUEENS QUAY - PLOT 7, CLYDEBANK | 249380 | 670232 | 2.6 | 2003 | LDP | Consented (PPiP) | SHIP site. Capacity changed from 98 to 100 to reflect SHIP @2024. @2025 - No longer ship site, programming moved back a year | DC15/234 | 2016-08-28 | Not yet started |  | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 40 | 0 | 0 | 0 | medium-term | Affordable | 0 | 100 |  |  | Deliverable with constraints | Financial: industry are citing issues with the marketability of the site. | Continue participating in Scottish Governments stalled sites programme. Planning and Regneration teams within council to work to promote West Dunbartonshire as location for housebuilding. WDC Housing to work with landowner and developers to enable delivery of affordable housing on site. | Mixed ownership | WDC | Brownfield | Yes |  | Disputed by Homes for Scotland
WD0544 | BOQUHANRAN ROAD | H2(51) | BOQUHANRAN ROAD, CLYDEBANK | 248939 | 670824 | 0.8 | 2009 | LDP | No Consent | @ 2025 site removed from SHIP. Programming removed |  |  | Not yet started |  | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | 0 | 34 |  |  | Constrained | Financial: Currently lacks funding commitment to deliver the site. It has been removed from SHIP. Land Use Status: Site is allocated in LDP2, but no active planning permission | WDC Housing to seek developers to deliver site | Private Owner | CLYDEBANK HA | Brownfield | Yes |  | No dispute
WD0489 | CABLE DEPOT ROAD SOUTH | H2(9) | CABLE DEPOT ROAD SOUTH, CLYDEBANK | 249146 | 670354 | 3.26 | 2005 | LDP | No Consent |  |  |  | Not yet started |  | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Long-term | Market | 200 | 0 |  |  | Constrained | Financial: industry are citing issues with the marketability of the site. | Continue participating in Scottish Governments stalled sites programme. Planning and Regneration teams within council to work to promote West Dunbartonshire as location for housebuilding | Private Owner | NK | Brownfield | Yes |  | No dispute
WD0546 | MELBOURNE AVE/SALISBURY PL Phase 1 | H2(3) | MELBOURNE AVE/SALISBURY PL Phase 1, CLYDEBANK | 247840 | 672193 | 0.48 | 2010 | LDP | No Consent |  |  |  | Not yet started |  | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | 0 | 25 |  |  | Constrained | Physical: Steep slope Land Use Status: Site is allocated in LDP2, but no active planning permission | Planning Authority continue to monitor site | West Dunbartonshire Council | NK | Brownfield | Yes |  | No dispute
WD0548 | LAND AROUND FOOTBALL STADIUM |  | LAND AROUND FOOTBALL STADIUM, DUMBARTON | 240069 | 674743 | 3.44 | 2010 | Windfall | Consented (full) | @2024 Mapping changed to improve accuracy DC19/127 Application pending - to extend permission and change to compliance with a condition on permission DC19/127. | DC19/127 | 2019-12-18 | Not yet started |  | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 37 | 0 |  |  | Constrained | Land Use Status: No allocated in LDP. No active planning permission | Continue to monitor site. Remove from audit in event that application to extend planning permission is not granted. | Private Owner | NK | Brownfield | No |  | No dispute
WD0552 | OLD MILL GARAGE | H2(35) | OLD MILL GARAGE, HARDGATE | 249770 | 672885 | 0.44 | 2011 | LDP | No Consent | Site has pending application for industrial unit, making progress of housing unclear - remove from effective supply in 2024 audit. |  |  | Not yet started |  | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 12 | 0 |  |  | Constrained | Land Use Status: Application pending for industrial unit. On site at time of audit. Physical: Site is at risk of flooding | Planning Authority to continue to monitor site. Remove from audit if industrial unit permitted. | Private Owner | NK | Brownfield | No |  | No dispute
WD0556 | MITCHELL WAY | H2(51) | MITCHELL WAY, ALEXANDRIA | 239156 | 680025 | 0.18 | 2012 | LDP | No Consent | 2023-2028SHIP site but with no capacity or . @ 2024 Flats along Mitchell Way have now been demolished and Lidl is under construction. A portion of the site remains, but capacity needs to be reassessed. Site in 2025-30 SHIP, but not seen as deliverable within the short to medium term. @ 2025 No progress made on the site. Site has been removed from SHIP |  |  | Not yet started |  | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | 0 | 26 |  |  | Constrained | Land Use Status: Allocated in LDP, but no active planning permission Financial: Currently lacks funding commitment to deliver the site. It has been removed from SHIP. | Planning authority to continue to monitor site. WDC Regeneration and Housing to progress ideas for the site following community consultation. | West Dunbartonshire Council | NK | Brownfield | No |  | No dispute
WD0563 | RADNOR PARK HOTEL | H2(12) | RADNOR PARK HOTEL, CLYDEBANK | 249744 | 671544 | 0.31 | 2013 | LDP | No Consent | @ 2025 site removed from SHIP |  |  | Not yet started |  | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | 0 | 28 |  |  | Constrained | Financial: Currently lacks funding commitment to deliver the site. It has been removed from SHIP. | WDC Housing seeking potential developers to bring the site forward. | Private Owner | NK | Brownfield | No |  | No dispute
WD0564 | BOWLING BASIN | H2(6) | BOWLING BASIN, BOWLING | 245290 | 673427 | 1.69 | 2013 | LDP | Consented (PPiP) |  | DC15/270 |  | Not yet started |  | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 75 | 0 |  |  | Constrained | Ownership: Not clear if owner, Scottish Canals, intends to complete partially implimented permission | Planning Authority to seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | NK | Brownfield | No |  | No dispute
WD0588 | FORMER CLYDEBANK HEALTH CENTRE | H2(36) | FORMER CLYDEBANK HEALTH CENTRE, CLYDEBANK | 249714 | 671478 | 1.04 | 2016 | LDP | No Consent | Health centre has been demolished. 2025/30 SHIP priority site. Programming from SHIP |  |  | Not yet started |  | 41 | 41 | 0 | 0 | 0 | 20 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | 0 | 41 |  |  | Deliverable | No known constraints | No actions required | Other Owner | WDC | Brownfield | No |  | Disputed by Homes for Scotland
WD0565 | SCOTTS YARD | H2(2) | SCOTTS YARD, BOWLING | 244243 | 673632 | 2.32 | 2013 | LDP | No Consent |  |  |  | Not yet started |  | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 75 | 0 |  |  | Constrained | Physical: Site at high risk of coastal flooding Land Use: Site is allocated in LDP2, but no active planning permission | Planning Authority continue to monitor site delivery | Private Owner | NK | Brownfield | Yes |  | No dispute
WD0599 | RHI SITE - STANFORD STREET | H2(38) | RHI SITE - STANFORD STREET, CLYDEBANK | 250490 | 670244 | 3.09 | 2018 | LDP | Consented (full) | Consultation with HfS in 2024 note that site is currently on hold. Commencement of enabling works expected in 2025. | DC19/186 |  | Started on site |  | 135 | 135 | 0 | 0 | 0 | 10 | 30 | 30 | 30 | 30 | 5 | 0 | 0 | 0 | short-medium-term | Market | 135 | 0 |  |  | Deliverable | No known constraints | Planning Authority continue to monitor site | Private Owner | TURNBERRY HOMES | Brownfield | No |  | No dispute
WD0570 | HILLVIEW | H2(31) | HILLVIEW, MILTON | 242672 | 674480 | 0.34 | 2014 | LDP | Consented (full) |  | 16/146 |  | Not yet started |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  | Market | 4 | 0 |  |  | Constrained | Land Use Status: Allocated in LDP but no active planning permission. | Planning Authority to continue to monitor site. | Private Owner | PLOTS | Brownfield | No |  | No dispute
WD0573 | SANDPOINT MARINA | H2(15) | SANDPOINT MARINA, DUMBARTON | 239759 | 674837 | 3.9 | 2014 | LDP | No Consent | Currently being used as a construction compound. Height of land has been increased significantly |  |  | Not yet started |  | 87 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 87 | 0 |  |  | Constrained | Land Use Status: Allocated in LDP but no active planning permission. Site currently under use as construction compound. Physical: Site at high risk of coastal flooding. | Planning Authority to continue to monitor site. | Private Owner | NK | Brownfield | No |  | No dispute
WD0604 | DICKENS AVENUE |  | DICKENS AVENUE, CLYDEBANK | 248910 | 671680 | 0.03 | 2020 | Windfall | No Consent | @2025 Discussions taking place between landowner (council) and developer. |  |  | Not yet started |  | 22 | 22 | 0 | 0 | 0 | 12 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 22 | 0 |  |  | Deliverable with constraints | Land Use Status: Allocated in LDP but no active planning permission | Planning Authority continue to monitor site | West Dunbartonshire Council | TURNBERRY HOMES | Brownfield | No |  | Disputed by Homes for Scotland
WD0575 | STANFORD STREET (COUNCIL DEPOT) | H2(6) | STANFORD STREET (COUNCIL DEPOT), CLYDEBANK | 250178 | 670135 | 2.12 | 2014 | LDP | No Consent |  |  |  | Not yet started |  | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 120 | 0 |  |  | Constrained | Ownership: Site is still in use as a depot Land Use Status: Site allocated in LDP but no planning permission | Planning Authority continue to monitor site | West Dunbartonshire Council | NK | Brownfield | No |  | No dispute
WD0581 | COCHNO WATERWORKS | H2(37) | COCHNO WATERWORKS, HARDGATE | 249480 | 673823 | 0.67 | 2015 | LDP | No Consent |  |  |  | Not yet started |  | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 11 | 0 |  |  | Constrained | No known constraints, however no works appear to have been carried out on site other than fencing site off | Planning Authority to continue to monitor site. Planning Authority to seek information from landowner as to delivery constraints. | Private Owner | NK | Brownfield | Yes |  | No dispute
WD0611 | DUNTIGLENNAN, FARM ROAD |  | DUNTIGLENNAN, FARM ROAD, CLYDEBANK | 248821 | 673368 | 8.84 | 2022 | Windfall | Consented (full) | @2025 site progressing | DC22/049/MSC | 2023-01-31 | Not yet started |  | 99 | 99 | 0 | 0 | 25 | 38 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | short-term | Market | 99 | 0 |  |  | Deliverable | No known constraints | Developer to continue progressing site. Planning Authority continue to monitor site | Private Owner | BARRATT HOMES | Greenfield | No |  | No dispute
WD0612 | FORMER PLAYDROME SITE |  | FORMER PLAYDROME SITE, CLYDEBANK | 249100 | 670200 | 3.56 | 2023 | Windfall | Consented (full) | @2025 Homes under construction. Foundations laid for first block and some walls going up @2024 capacity updated to match planning permission | DC23/149/FUL | 2024-04-15 | Started on site |  | 128 | 128 | 0 | 0 | 39 | 54 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | short-term | Market | 128 | 0 |  |  | Deliverable | No known constraints | Developer to continue progressing site. Planning Authority continue to monitor site | West Dunbartonshire Council | MILLER HOMES | Brownfield | Yes |  | No dispute
WD0479 | AULD STREET Ph 2 | H2(52) | AULD STREET Ph 2, DALMUIR | 248387 | 671008 | 0.4 | 2004 | LDP | No Consent |  |  |  | Not yet started |  | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Medium-term | Affordable | 0 | 16 |  |  | Deliverable | Land Use Status: Application DC21/174/FUL decision pending. Council minded to grant subject to section 75 agreement. | Developer and Planning Authority to finalise Section 75 agreement. Planning Authority continue to monitor site | Private Owner | NK | Brownfield | Yes |  | No dispute
WD0401 | CRAIGEND HOUSE, CARDROSS ROAD | H2(22) | CRAIGEND HOUSE, CARDROSS ROAD, DUMBARTON | 238217 | 675630 | 4.96 | 1998 | LDP | Consented (full) | Under construction. Some homes appear complete externally | DC/21/211/FUL | 2022-09-14 | Started on site |  | 81 | 81 | 0 | 0 | 38 | 38 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 81 | 0 |  |  | Deliverable | No known constraints | Developer to continue progressing site. Planning Authority continue to monitor site | Private Owner | MILLER HOMES | Brownfield | Yes |  | No dispute
WD0589 | MOUNT PLEASANT HO. ASHTREE COURT | H2(32) | MOUNT PLEASANT HO. ASHTREE COURT, OLD KILPATRICK | 246533 | 672839 | 0.38 | 2016 | LDP | Consented (full) | 2025/30 SHIP priority site. @2024 capacity updated to match SHIP. Grant from Affordable Housing Supply Programme | DC23/146/FUL | 2023-12-22 | Completed |  | 19 | 0 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Affordable | 0 | 19 |  |  |  |  | Planning Authority to remove from audit | West Dunbartonshire Council | WDC | Brownfield | No |  | No dispute
WD0482 | SHED 7 CASTLE RD |  | SHED 7 CASTLE RD, DUMBARTON | 240286 | 674623 | 5.08 | 2005 | Other | Consented (full) | At march 2023, Phases 1 & 2 complete. Phase 3 comprises 6 flatted blocks and 16 houses. 16 houses complete. Block 4 complete and partially occupied (5 units at May 2023). Blocks 5 & 6 well out of the ground. Blocks 7,8 & 9 at founds. At September 2024 Block 5 complete and mostly occupied, with remaining flats able to be occupied. For sale signs in block 6 and some signs of occupation, however internal works taking place in some flats. Block 7 construction underway. 8 and 9 not yet beyond foundations. At 2025 Final two blocks of flats under construction (blocks 8 and 9) and emaining flats ready for occupation. | DC19/096 | 2019-10-23 | Started on site |  | 219 | 30 | 17 | 189 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 219 | 0 |  |  | Deliverable | No known constraints | Developer to continue progressing site. Planning Authority continue to monitor site | Private Owner | TURNBERRY HOMES | Brownfield | No |  | No dispute
WD0551 | FORMER COTTAGE HOSPITAL, PARK CRES | H2(59) | FORMER COTTAGE HOSPITAL, PARK CRES, DUMBARTON | 239960 | 676026 | 0.26 | 2011 | LDP | No Consent | Development brief prepared Site in 2025-30 SHIP, but not seen as deliverable within the short to medium term. |  |  | Not yet started |  | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | Long-term | Affordable | 0 | 10 |  |  | Deliverable with constraints | Financial: SHIP states that site is not deliverable within short to medium term due to funding availability. | WDC Housing to seek funding from Affordable Housing Supply Programme. Planning Authority continue to monitor site | West Dunbartonshire Council | NK | Brownfield | Yes |  | No dispute
WD0591 | adj 102 EAST BARNS STREET | H2(7) | adj 102 EAST BARNS STREET, CLYDEBANK | 250853 | 669380 | 0.07 | 2017 | LDP | Consented (full) | Permission lapsed in 2025 | DC19/141 | 2020-12-23 | Not yet started |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 4 | 0 |  |  | Constrained | Land Use Status: Allocated in LDP but no active planning permission | Planning Authority to seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | NK | Brownfield | No |  | No dispute
WD0578 | HAWTHORNHILL ROAD | H2(23) | HAWTHORNHILL ROAD, DUMBARTON | 238306 | 675907 | 3.26 | 2015 | LDP | Consented (full) | Under construction. Some homes nearing completion | DC22/072/FUL |  | Started on site |  | 68 | 30 | 13 | 38 | 29 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 68 | 0 |  |  | Deliverable | No known constraints | Planning Authority to continue to monitor site. | West Dunbartonshire Council | PERSIMMON | Brownfield | Yes |  | No dispute
WD0592 | CROSSLET ESTATE | H2(17) | CROSSLET ESTATE, DUMBARTON | 241202 | 675350 | 0.74 | 2017 | LDP | No Consent | Pre-app discussions have taken place with applicant |  |  | Not yet started |  | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | Medium-term | Market | 6 | 0 |  |  | Deliverable | No known constraints | Planning Authority continue any discussions as part of pre-app process. Developer to progress and submit pplanning application to Planning Authority Planning Authority to continue to monitor site. | West Dunbartonshire Council | PLOTS | Greenfield | No |  | No dispute
WD0608 | BELLSMYRE REDEVELOPMENT, PHASES 1-3 |  | BELLSMYRE REDEVELOPMENT, PHASES 1-3, DUMBARTON | 240847 | 676542 | 4.87 | 2022 | Windfall | Consented (full) | Construction started on phase 1. Demolitions in phase 2 complete. Flats in phase 3 still in place. 2025/30 SHIP priority site. Grant from Affordable Housing Supply Programme. Programming from SHIP. | DC21/244/FUL | 2022-02-16 | Not yet started |  | 138 | 138 | 0 | 0 | 0 | 33 | 27 | 30 | 30 | 18 | 0 | 0 | 0 | 0 | Short-term | Affordable | 0 | 138 |  |  | Deliverable | No known constraints | Planning Authority to continue to monitor site. | Housing Association | CALEDONIA HA | Brownfield | No |  | No dispute
WDDB0302A | FORMER LEVEN SHIPYARD | H2(18) | FORMER LEVEN SHIPYARD, DUMBARTON | 240070 | 674903 | 3 | 1991 | LDP | Consented (full) | 2023 - split this from completed part of site to just leave balance of development land. | 16/229 |  | Not yet started |  | 130 | 130 | 0 | 0 | 0 | 10 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | short-medium-term | Market | 130 | 0 |  |  | Deliverable | No known constraints. Site has permission that could be implimented. Planning application to change house types is currently pending. | Planning authority and developer to resolve application to change housing types. Planning Authority to continue to monitor site. | Private Owner | TURNBERRY HOMES | Brownfield | Yes |  | No dispute
WD0598 | FAIFLEY BOWLING CLUB | H2(63) | FAIFLEY BOWLING CLUB, FAIFLEY | 250419 | 672935 | 1.02 | 2018 | LDP | Consented (full) | 2025/30 SHIP priority site. Programming from SHIP @2024 capacity updated to match planning permission | DC23/083/FUL | 2023-10-14 | Not yet started |  | 27 | 27 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | 0 | 27 |  |  | Deliverable | No known constraints | Developer to progress site Planning Authority to continue to monitor site. | West Dunbartonshire Council | KNOWES HA | Brownfield | No |  | No dispute
WD0450 | HARDGATE HALL | H2(28) | HARDGATE HALL, HARDGATE | 249761 | 672859 | 0.1 | 2005 | LDP | Consented (full) |  | DC20/121 | 2020-10-08 | Not yet started |  | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 5 | 0 |  |  | Deliverable | No known constraints | Planning Authority to continue to monitor site. | Private Owner | NK | Brownfield | No |  | No dispute
WD0593 | CHURCH STREET FORMER COUNCIL OFFICE | H2(33) | CHURCH STREET FORMER COUNCIL OFFICE, ALEXANDRIA | 239194 | 679890 | 0.26 | 2018 | LDP | No Consent | Site has been sold by WDC and being retained as serviced accomodation. |  |  | Not yet started |  | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 15 | 0 |  |  | Constrained | Ownership: Business uses still on site. Recent planning application to change from class 4 (office) to business centre (Sui generis) indicates there is no intent to deliver housing on the site. Land Use Status: No active planning permission for housing | Planning Authority to seek further information from site owner as to their intent with the site and any potential constraints. | Private Owner | NK | Brownfield | No |  | No dispute
WD0594 | HARDGATE HEALTH CENTRE | H2(40) | HARDGATE HEALTH CENTRE, HARDGATE | 249732 | 672562 | 0.13 | 2018 | LDP | No Consent |  |  |  | Not yet started |  | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 6 | 0 |  |  | Constrained | No known constraints | Planning Authority to continue to monitor site. Planning Authority to seek information from landowner as to delivery constraints. | Other Owner | NK | Brownfield | No |  | No dispute
WD0596 | MAIN STREET | H2(40) | MAIN STREET, JAMESTOWN | 239680 | 681224 | 0.19 | 2018 | LDP | No Consent |  |  |  | Not yet started |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 4 | 0 |  |  | Constrained | Land Use Status: Allocated in LDP but no active planning permission. | Planning Authority to continue to monitor site. | Private Owner | NK | Greenfield | Yes |  | No dispute
WD0597 | GLEBE | H2(41) | GLEBE, OLD KILPATRICK | 246305 | 672932 | 1.08 | 2018 | LDP | No Consent |  |  |  | Not yet started |  | 15 | 15 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 15 | 0 |  |  | Deliverable with constraints | Land Use Status: Allocated in LDP but no active planning permission. Ownership: Lack of activity on site or enquiries from site owner/developer shows lack of intention to develop site. | Planning Authority to seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | NK | Greenfield | No |  | Disputed by Homes for Scotland
WD0541 | LEVENBANK ROAD | H2(29) | LEVENBANK ROAD, JAMESTOWN | 239940 | 681194 | 2.18 | 2009 | LDP | No Consent |  |  |  | Not yet started |  | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Medium-term | Market | 60 | 0 |  |  | Deliverable with constraints | Land Use Status: Allocated in LDP but no active planning permission. Physical: Access road is not adopted | While not adopted, the access road is owned by WDC. WDC Roads and Planning continue to work with potential developer on access solution on neighbouring site. | Private Owner | NK | Greenfield | Yes |  | No dispute
WD0602 | CLYDEBANK EAST | H2(31) | CLYDEBANK EAST, CLYDEBANK | 250743 | 669157 | 3.2 | 2020 | LDP | Consented (full) | @2025 complete 2025/30 SHIP priority site. Grant from Affordable Housing Supply Programme | DC21/138/FUL | 2022-06-08 | Completed |  | 88 | 0 | 88 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | 0 | 88 |  |  |  | 0 | Planning Authority remove site from housing land audit. | West Dunbartonshire Council | WDC | Brownfield | No |  | No dispute
WD0603 | FRANK DOWNIE HOUSE | H2(24) | FRANK DOWNIE HOUSE, CLYDEBANK | 247765 | 671559 | 0.31 | 2020 | LDP | No Consent | No allocation, no permission, remove from audit. |  |  | Not yet started |  | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 20 | 0 |  |  | Constrained | Land Use Status: Not Allocated in Local Plan. No active planning permission | Planning Authority remove site from housing land audit. | West Dunbartonshire Council | NK | Brownfield | No |  | No dispute
WD0605 | QUEEN MARY DAY CARE CENTRE |  | QUEEN MARY DAY CARE CENTRE, CLYDEBANK | 250650 | 670790 | 0.3 | 2020 | Windfall | No Consent | 2025/30 SHIP priority site. @2025 capacity changed to reflect SHIP. Site is currently going through pre-app and design process. |  |  | Not yet started |  | 16 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | 0 | 16 |  |  | Deliverable | Land Use Status: No Allocation and no planning permission, but may be permissable through criteria in NPF4 Policy 16 f) criteria | Planning Authority continue to monitor site | West Dunbartonshire Council | NK | Brownfield | No |  | No dispute
WD0613 | PAPPERT | H2(14) | PAPPERT, BONHILL | 240368 | 679392 | 1.36 | 2024 | LDP | Consented (full) | Site Complete @2025 2025/30 SHIP priority site. Grant from Affordable Housing Supply Programme | DC23/102/FUL | 2023-09-20 | Completed |  | 26 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | 0 | 26 |  |  |  | 0 | Planning authority to remove site from housing land audit. | West Dunbartonshire Council | WDC | Brownfield | No |  | No dispute
WDDB0300A | DALQUHURN | H2(61) | DALQUHURN, RENTON | 239195 | 677748 | 2.56 | 1991 | LDP | Consented (full) | 2025/30 SHIP priority site (SHOWS CAPACITY OF PHASES 5 & 6 AS 50) | DC08/033/FUL | 2008-06-03 | Not yet started |  | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 25 | 0 | 0 | medium-long-term | Market | 125 | 0 |  |  | Deliverable | No known constraints | Planning Authority to continue to monitor site. | Housing Association | NK | Brownfield | No |  | No dispute
WDDB0300D | DALQUHURN PHASE 4 | H2(61) | DALQUHURN PHASE 4, RENTON | 239195 | 677748 | 0.7 | 1996 | LDP | Consented (full) | 2025/30 SHIP priority site. Grant from Affordable Housing Supply Programme. Completed homes are occupied. Remaining homes near completion with heras fence still around them. Signs of construction traffic and works internally are taking place. | DC18/233 | 2019-06-03 | Started on site |  | 25 | 18 | 7 | 7 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | 0 | 25 |  |  | Deliverable | No known constraints | Developer to continue progressing site. Planning Authority to continue to monitor site. | Housing Association | CALEDONIA HA | Brownfield | No |  | No dispute